## Feuil1
LOGBOOK
VSEAT
Brice Berclaz & Aurélien May |  |  |  |  | Allocation of tasks (part 1 to part 2)
[5 empty] | ID | Description | Name | Status
DATE | ALLOCATION | EVENT | PROBLEM | SOLUTION | 1 | Session | Aurélien | Completed
2019-10-18 | BOTH | Github repository created, first commit | - | - | 2 | Login & access management | Aurélien | Completed
2019-10-18 | Brice | Local DB created | - | - | 5 | Staff interface | Aurélien | Completed
2019-10-18 | Brice | Export DB into the server | - | - | 7 | Order details staff | Aurélien | Completed
2019-10-28 | 50/50 | DTO created | - | - | 10 | Global design | Aurélien | In progress
2019-10-28 | 50/50 | BLL created | - | - | 3 | Customer order | Brice | Completed
2019-10-28 | 50/50 | DAL created | - | - | 4 | Shopping cart | Brice | Completed
2019-10-28 | 50/50 | ConsoleApplication updated | - | - | 6 | Order details customer | Brice | Completed
2019-10-05 | BOTH | DAL/BLL/DTO/ConsoleApp terminated | - | - | 8 | Conditions (time 15', <5 order each 30') | Brice | Completed
2019-10-05 | BOTH | Final test for part 1 | - | - | 9 | Cancel order | Brice | In progress
2019-11-06 | BOTH | Hand back: Part 1 (BLL/DAL/DTO/ConsoleApp+DB) | - | - | 11 | Readme | Brice | In progress
2019-10-18 | Brice | WebApplication created with basic controllers and models | - | -
2019-12-05 | Brice | Controllers creation | Circular dependency | Added scoped in startup + implemented DAL insted of BLL itself in the BLL (management error)
2019-12-06 | Aurélien | Login added (dev) | - | -
2019-12-07 | Brice | Dish management | Shopping cart | Static list of dishes
2019-12-07 | Aurélien | Login - DB
2019-12-15 | BOTH | Hand back: Part 2 (entire project) | - | -
2019-12-07
Effective logbook on Github
https://github.com/Bearbrice/BerclazMayVSEat