## Logbook
LOGBOOK
VSEAT
Effective Logbook on : https://github.com/Bearbrice/BerclazMayVSEat
Brice Berclaz & Aurélien May
DATE | ALLOCATION | EVENT | PROBLEM | SOLUTION | Allocation of tasks (part 1 to part 2)
2019-10-18 | BOTH | DAL/BLL/DTO/ConsoleApp terminated | - | - | ID | Description | Name | Status
2019-10-18 | BOTH | Final test for part 1 | - | - | 1 | Session | Aurélien | Completed
2019-10-18 | BOTH | Github repository created, first commit | - | - | 2 | Login & access management | Aurélien | Completed
2019-10-21 | 50/50 | Local DB created | - | - | 5 | Staff interface | Aurélien | Completed
2019-10-21 | Brice | Export DB into the server | - | - | 7 | Order details staff | Aurélien | Completed
2019-11-11 | BOTH | WebApplication created with basic controllers and models | - | - | 10 | Global design | Aurélien | Completed
2019-10-28 | 50/50 | DTO created | - | - | 11 | Readme | Aurélien | Completed
2019-10-28 | 50/50 | BLL created | - | - | 3 | Customer order | Brice | Completed
2019-10-28 | 50/50 | DAL created | - | - | 4 | Shopping cart | Brice | Completed
2019-10-28 | 50/50 | ConsoleApplication updated | - | - | 6 | Order details customer | Brice | Completed
2019-11-06 | BOTH | Hand back: Part 1 (BLL/DAL/DTO/ConsoleApp+DB) | - | - | 8 | Conditions (time 15', <5 order each 30') | Brice | Completed
2019-12-05 | Brice | Controllers creation | Circular dependency | Added scoped in startup + implemented DAL insted of BLL itself in the BLL (management error) | 9 | Cancel order | Brice | Completed
2019-12-06 | Aurélien | Login added (dev) | - | -
2019-12-07 | Aurélien | Login - DB | - | -
2019-12-07 | Aurélien | Get orders for Staff | - | -
2019-12-07 | Brice | Dish management | Shopping cart | Static list of dishes
2019-12-08 | Brice | Add an delete dishes from shopping cart | - | -
2019-12-10 | Aurélien | Management staff deliveries | - | -
2019-12-10 | Aurélien | Login adjustements and design making | - | -
2019-12-10 | Brice | Add an order with time chosen | - | -
2019-12-10 | Brice | Order confirmation managed | - | -
2019-12-11 | Aurélien | Staff can display order details | Access information | Creation of model to store information
2019-12-11 | Brice | Test added on datetime scheduled | - | -
2019-12-12 | Aurélien | Login management and errors avoidance | - | -
2019-12-12 | Brice | Assign a staff to and order with constraint | - | -
2019-12-13 | Aurélien | Delivery time finishing touch for staff | - | -
2019-12-13 | Brice | Redirection links in pages and design customer part | - | -
2019-12-14 | Aurélien | Create account (login and datas for customer side) | - | -
2019-12-14 | Aurélien | Global design | - | -
2019-12-14 | Brice | Cancellation of orders | - | -
2019-12-15 | Aurélien | Readme done | - | -
2019-12-15 | BOTH | Feeding the database | - | -
2019-12-15 | BOTH | Code cleaning | - | -
2019-12-15 | BOTH | Errors prevention when new customer created | - | -
2019-12-15 | Brice | Logbook done | - | -
2019-12-15 | BOTH | Hand back: Part 2 (entire project) | - | -
Recall : effective logbook on Github
https://github.com/Bearbrice/BerclazMayVSEat